## Improvement Plan
CSP Grant Community School Sponsor Quality Improvement Action Plan
Sponsor: | Cleveland Municipal School District |  | Submission Date: |  | 2020-01-10
Plan Line Number | Performance Measure/ Standard | 2018-2019 3-Point Requirement | Improvement Goal | Strategy | Action | Person(s) Responsible | Estimated Date of Completion | Documentation / Evidence of Completion
Number plan lines consecutively | Enter the name of the Quality Practices Standard with Item Number | Enter the applicable exemplary standard from the Quality Practices rubric | Enter the sponsor's improvement goal for the listed performance measure or standard | Enter the Strategy the sponsor will take to meet the stated Improvement Goal | Enter the Action the sponsor will take to meet the stated Improvement Goal | Enter the name and/or role of the person(s) responsible for meeting the stated improvement goal, strategy and action steps | Enter the estimated date on which the stated improvement goal will be met | Describe the documentation that will be used as evidence of completion of the stated improvement goal or individual action(s)
1 | D.03 | The sponsor submitted evidence of having conducted at least two on-site reviews (beyond the monthly enrollment and financial reviews), at least three months apart while school is in session, for all selected schools regarding the school’s compliance with all applicable laws, rules, contractual obligations and academic performance measures and During the on-site review, data are collected from a school employee on the day of the review and The sponsor submitted evidence of an on-site visit protocol and The sponsor submitted evidence that it collects data from school employees, including at least one administrator and one or more instructors The submitted on-site visit protocol includes observation guidelines and specifies how interviews will be conducted and The sponsor submitted evidence that it collects data from at least three stakeholder groups (e.g., the school’s governing authority members, students, parents, staff, management company staff, etc.) over the course of the review year. | As of 2019-20, the sponsor will meet at least the 3 point requirement. | Sponsor will review reviewer feedback and results from 18-19 and and review site visit protocols and reports to identify any deficiencies. | Sponsor will revise site visit protocols and report formats as necessary to address any deficiencies. Reviewer notes from 18-19 show that reviewers were not able to identify that our site visits address school academic indicators or performance. | Matt Rado (Executive Director, Charter Schools), Anna Turner (Director, Charter Schools) | 2019-12-01 | Site visit reports
2 | D.04 | The sponsor submitted evidence of providing each selected school with a report (beyond the monthly financial and enrollment review reports) following each of two on-site reviews conducted while school is in session and at least three months apart regarding the school’s compliance with all applicable laws, rules, contractual obligations and academic performance measures and If the sponsor identifies an area needing improvement, the report cites that the school must take action and Each submitted report includes the information collected, a summary of findings and, if applicable, areas needing improvement and If the sponsor identifies an area needing improvement, it specifies the steps or timeframes for doing so and requests and reviews status updates from the school regarding its progress in the area and Each submitted report recognizes each school's areas of strength. | As of 2019-20, the sponsor will meet at least the 3 point requirement. | Sponsor will review reviewer feedback and results from 18-19 and and review site visit protocols and reports to identify any deficiencies. | Sponsor will revise site visit protocols and report formats as necessary to address any deficiencies. Reviewer notes from 18-19 show that reviewers were not able to identify that our site visits address school academic indicators or performance. | Matt Rado (Executive Director, Charter Schools), Anna Turner (Director, Charter Schools) | 2019-12-01 | Site visit reports