## Ohio
Ohio Department of Education U282A150023
CSP Grant
| Project Director: |  | Rashaun Holliman
| Program Officer: |  | Kathryn Meeley
| High-Risk Condition Start Date: |  | 2016-09-14 | time axis 2017-05-08 to 2017-07-03
| Display Week: |  | 35 |  |  |  |  | 2017-05-08: Week 35; 2017-05-15: Week 36; 2017-05-22: Week 37; 2017-05-29: Week 38; 2017-06-05: Week 39; 2017-06-12: Week 40; 2017-06-19: Week 41; 2017-06-26: Week 42
| UPDATED 06/28/2017 | [6 empty] | 2017-05-08: 2017-05-08; 2017-05-15: 2017-05-15; 2017-05-22: 2017-05-22; 2017-05-29: 2017-05-29; 2017-06-05: 2017-06-05; 2017-06-12: 2017-06-12; 2017-06-19: 2017-06-19; 2017-06-26: 2017-06-26
WBS | Task | Lead | Start | End | Cal. Days | % Done | Work Days | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
1 | Advisory Committee
1.1 | Reprentative Identification | Ohio | 2016-09-14 | 2016-12-01 | 79 | 100% | 57
1.2 | Creation of Charter | Ohio | 2016-09-14 | 2016-12-01 | 79 | 100% | 57
1.3 | Approval of Charter (updated approval on 4/5/2017 original was | ED | 2016-12-02 | 2017-04-05 | 14 | 100% | 89
1.4 | Formation of Advisory Committee (1st meeting was 3/3/2017) | Ohio | 2017-01-03 | 2017-03-03 | 15 | 100% | 44
1.5 | [Task] |  | 2017-03-04 | 2017-03-05 | 2 | 50% | 0
1.6 | [Task] |  | 2015-03-24 | 2015-03-26 | 3 | 50% | 3
1.7 | [Task] |  | 2015-03-27 | 2015-03-31 | 5 | 50% | 3
1.8 | [Task] |  | 2015-04-01 | 2015-04-07 | 7 | 50% | 5
1.9 | [Insert Rows above this one, then Hide or Delete this row]
2 | Independent Monitor
2.1 | Develop Agreed Upon Procedures | Ohio | 2016-09-14 | 2017-02-08 | 79 | 100% | 106
2.2 | Approve Agreed Upon Procedures (approved on 2/8/17, modified and approved again on 04/24/17, must be finalized with independent monitor and reviewed by ED before complete) | ED | 2016-12-02 | 2017-06-06 | 14 | 100% | 133
2.3 | Release of RFP for independent Monitor | Ohio | 2016-12-16 | 2017-01-31 | 14 | 100% | 33
2.4 | Hiring of Independent Monitor | Ohio | 2016-12-30 | 2017-03-20 | 32 | 100% | 57
2.5 | Independent Monitor visit dates (tentative) | Ohio | 2017-07-07 | 2017-09-04 | 60 | 0% | 42
2.6 | Development and Delivery of Report to USED | Ohio | 2017-09-07 | 2017-10-16 | 40 | 0% | 28
3 | Itemized Budget
3.1 | 10 days of being notified of condition - updated budget | Ohio | 2016-09-14 | 2016-09-27 | 14 | 100% | 10
3.2 | March 2 update (N/A - no costs currently being incurred on the grant) | Ohio | 2017-02-22 | 2017-03-31 | 9 | 100% | 28
3.3 | September 1 update | Ohio | 2017-08-24 | 2017-09-01 | 9 | 0% | 7
3.4 | [Task] |  | 2017-08-25 | 2017-08-25 | 1 | 0% | 1
3.5 | [Insert Rows above this one, then Hide or Delete this row] |  |  | 0
4 | Quarterly Performance Reports
4.1 | October 1 (grant project timeline) (EXTENSION REQUESTED/Approved) | Ohio | 2016-09-14 | 2016-10-21 | 38 | 100% | 28
4.2 | January 1 (grant project timeline +report on obligations, expenditures, revenues, and activities) | Ohio | 2016-10-24 | 2016-12-27 | 71 | 100% | 47
4.3 | April 1 (grant project timeline) (EXTENSION REQUESTED/Approved) | Ohio | 2016-12-28 | 2017-04-14 | 91 | 100% | 78
4.4 | July 1 (grant project timeline +report on obligations, expenditures, revenues, and activities) | Ohio | 2017-04-15 | 2017-07-03 | 91 | 100% | 56
5 | Subgrant Competition
5.1 | Authorizer Evaluation and Quality Control | Ohio | 2016-09-14 | 2016-10-13 | 139 | 100% | 22
5.2 | subgrantee eligibility screening/Development of Scoring Rubric | Ohio | 2016-09-14 | 2017-02-17 | 139 | 100% | 113
5.3 | RFA process and copy of RFA | Ohio | 2017-02-17 | 2017-03-13 | 139 | 100% | 17
5.3.1 | Approval of the RFA by ED | ED | 2017-02-17 | 2017-04-10 | 7 | 100% | 37
5.3.2 | Notice of Grant Opportunity | Ohio | 2017-03-01 | 2017-04-20
5.3.3 | RFA Publish Date | Ohio | 2017-04-10 | 2017-05-18
5.3.4 | Projected Subgrant RFA release date and close date | Ohio | 2017-05-18 | 2017-06-15 | 30 | 100% | 21
5.4 | Subgrant award process | Ohio | 2017-06-19 | 2017-06-30 | 60 | 0% | 10
5.4.1 | pre-application training | Ohio | 2017-04-20 | 2017-05-17 | 30 | 100% | 20
5.4.2 | selection and training of reviewers | Ohio | 2017-05-23 | 2017-06-16 | 45 | 90% | 19
5.4.3 | budget reviews, internal screening, and risk assessment | Ohio | 2017-06-19 | 2017-07-03 | 60 | 100% | 11
5.4.4 | award determination process | Ohio | 2017-07-03 | 2017-07-07 | 60 | 0% | 5
5.5 | processing of subgrantee payments (written protocols) (Comprehensive Plan) | Ohio | 2016-09-14 | 2017-05-17 | 139 | 100% | 176
5.6 | Ensuring subgrantee adherence to all program requirements (written protocols) | Ohio | 2017-03-07 | 2017-04-17 | 139 | 100% | 30
6 | Subgrantee Monitoring Protocol
6.1 | Develop Subgrantee Monitoring Protocol | Ohio | 2017-03-07 | 2017-06-09 | 43 | 100% | 69
6.2 | Approve Subgrantee Monitoring Protocol | ED | 2017-06-09 | 2017-06-22 | 14 | 0% | 10
7 | Public List of Charter Schools
7.1 | Centralized listing will be updated Annually | Ohio | 2016-09-14 | 2017-06-25 | 90 | 50% | 203
1900-01-04
0.1 | [Insert Rows above this one, then Hide or Delete this row] |  | 2017-03-12
2017-06-14
1900-01-04
TEMPLATE ROWS |  |  | 2016-09-19
See the Help worksheet to learn how to use these rows. You can hide these rows before printing. |  |  | 1900-01-09
CATEGORY ROWS and WBS NUMBERING |  |  | 2017-03-17
1 | [ Task Category (label only) ] |  | 2017-06-19
1.1 | [ Level 2 Task ] |  | 1900-01-09
1.1.1 | . [ Level 3 Task ] |  | 2016-09-24
1.1.1.1 | . . [ Level 4 Task ] |  | 1900-01-14
Examples of ways to define the Start, End, and Duration of tasks |  |  | 2017-03-22
1 | [ Task Category (summary) ] |  | 2017-06-24 | 2016-09-29 | -267 |  | -192
2 | Milestone |  | 1900-01-14 | 2015-03-01
2.1 | [ Start Date and Calendar Days ] |  | 2016-09-29 | 2016-09-29 |  |  | 1
2.2 | [ Start Date and End Date ] |  | 1900-01-19 |  | 0 |  | 0
2017-03-27
8 | WestED Monitoring
6.1 | Initial Visit (tentative) | ED/WestED | 2017-02-27 | 2017-03-01 | 7 | 100% | 3
6.2 | Draft Technical Report | ED/WestED | 2017-05-17 | 2017-06-02 | 20 | 0% | 13
6.2 | 2nd Visit (tentative) | ED/WestED | 2017-11-02 | 2017-11-06 | 5 | 0% | 3
6.3 | Draft Technical Report | ED/WestED | 2017-11-09 | 2017-11-26 | 18 | 0% | 12